## Sheet1
		Dmitry	Vacations	Dmitry	Boud				Boud
				15-01 .. 28-01
Task			Estimated Effort
* Leftovers for the vector tools:			19d 1:00						Left-overs of scripting		?
	** Patterns		8d 4:00						gmic-qt plugin		5
		* Test loading and rendering patterns in Krita	4h						reference images tool		10
		* Remove usual KoPatternBackground and make automated loading of raster patterns into KoVectorPatternBackground.	1d 6:00						svg koresource + selector		5
		** KoPattern should provide two interfaces: image() for raster engines and shapes() for vector code.	4h						text tool/shape		?
		** KoPattern should be able to save/load SVG objects from resources folder	4h						palette manager		?
		** KoVectorPatternBackground will just fetch the shapes via shapes() all the time	4h						Intel: MS3 finger painting
		** Remove KoPatternBackground	2h						Intel: MS4: simple demo version
		* Port KoVectorPatternBackground to use regular KoPattern object	1d
		* Implement GUI for selecting standard Krita patterns	4d 2:00
		** Select from predefined patterns and pass shapes to the vector background	2d
		** Repeat strategy selector	4h
		** Edit reference point using a strategy	2h
		** Scale using the second handle	2h
		** Rotate when dragging from empty area	1d
		** When dragging handles: snap to original position	2h
		* "Group into pattern" action	06:00						Intel:
		** When groupng into a pattern, a dialog asks for a name for the new pattern.	4h						Start June 1st, finish October 1st
		** The docker should have some feature for selecting "recent" patterns.	2h						Remove bevel style from SOW
		** Question for painters: should the pattern'ed object be removed from the canvas?							Euros not dollars?
		* "Ungroup from pattern" action	02:00						MS2	3.2	end of june
		** Action from the context menu	1h						MS1	3.3	end of september
		** Action in the docker	1h						MS3	3.3
	** Filters		10d 5:00						MS4	3.3.1
		* Loading/saving of SVG filters	1w
		* Implement rendering tree for filters (incl. need/change rects)	3d
		* Implement a filter resource with saving/loading	1d
		* Import selected predefined filters from Inkscape	1h
		* Test predefined filters	4h
		* Implement a docker for selecting predefined filters	1d
* Text Tool			19d 4:00
	** Load and render text from SVG1 (1st iteration)		1.5w	I can do the rendering, the only thing you need to do is implement the loading/saving for now.
	** Save text to SVG1 (1st iteration)		2d
	** Load/render/save test from SVG2 (2nd iteration)		2w	We're going to stick with what Qt can render for the first version, so no need for this
	** Implement text on shape, text on path (low priority for now)
* Lazy brush			4d 0:00
	** Implement Watershed algorithm		3d	Weren't we going to re-use gmic's c++ algorithm here?
	** Connect it to the lazy brush		1d
* Stacked brushes			2w
* Intel Projects			53d 0:00	We're not sure of getting the project :-)			begin-september
	** Threaded marker brush		1w
	** Threaded faded brush		6w
	** Embed faded quick brush into Pixel Brush Engine		1w
	** Speed metric for the brushes in Krita		3d
	** Threaded cache regeneration		1w
	** Threaded frames rendering		1w
	** Dmitry implements selection of the number of threads on the runtime		0.01d
* Async saving			5d 0:00
	** Finish async saving		4d
	** Postpone closing of the window with sigSavingFinished		1d